TABULAM PUBLIC SCHOOL

School  Plan

2010 - 2012

A participant in the Schools In Partnership initiative

We will:

1. Value, respect and appreciate Aboriginal culture and student identity as an intrinsic part of each school community’s culture

2. Develop genuine partnerships and engagement with Aboriginal parents, communities and interagency groups

3. Maximise educational outcomes for each Aboriginal student

4. Support quality teaching practices to better engage Aboriginal students

5. Increase successful engagement and participation of all students in education and training

1. School context:

Tabulam Public School (enrolment 66) has a diverse school community characterised by a significant (60%) Aboriginal enrolment, isolation and socio-economic disadvantage. The school has a strong partnership with the local community and a strong focus on student achievement. NAPLAN data indicates that while many students have succeeded and growth is strong, there is a need to continue to address the literacy and numeracy outcomes of students.

2. School purpose

To improve outcomes for all students through programmed Quality Teaching practices. To improve outcomes for all students through strong and effective home/school/pre-school partnerships. To increase the engagement and enjoyment of all students in the learning process. To improve learning outcomes for Aboriginal students.

3. Long-term school strategic directions (3 year horizon)

To embed Quality Teaching strategies in literacy and numeracy programs. To improve attendance levels to reach regional/state average. To have Aboriginal student outcomes equal or better the state average. To increase parental involvement in the education process.

4. Shorter-term school strategic goals (1 year horizon)

To improve outcomes in literacy (focus on writing) To improve outcomes in numeracy (focus on mental computation and mathematical language) To review and implement Personal Learning Plans for all students. To embed Aboriginal perspectives across the curriculum. To embed technology across the curriculum.

5. Total school budget, all sources: $359136.00

The plan has been endorsed and approved by: Selwyn Nix School Education Director, Richmond Valley Network

| Principal: | Lesley Mills | Date: 18/11/2010 |  | School Education Director: | Selwyn Nix | Date: |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Principal’s initials: _______________

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Schools In Partnership Outcome Nos:1 and 3 To improve literacy and numeracy outcomes for Aboriginal students. 20% Yr 5 Aboriginal students in band 6,7&8 NAPLAN in literacy and numeracy PLPs implemented with 100% Aboriginal students in 2009 10% increase in Aboriginal students reading at stage appropriate level 10% increase in comprehension levels of Aboriginal students |  | Language Enrichment Program Embedding technology into literacy and numeracy programs AERT team teaching reading Implementation of Accelerated Literacy Program Prof Dev in reading strategies Weekly teaching focus in learning to and learning about reading, writing and talking and listening. PLP’s with all students & carers Explicit, timetabled talking and listening programs Literacy based Aboriginal Studies in all classes Trained Aboriginal Assistants in classes Homework Centre-Liaising with Youth workers. Weekly Aboriginal Education Committee meetings Active local AECG and attendance at Regional AECG Dare To Lead Action Plan-including school snapshot and prof dev of all staff Adult Technology training Group | 100% students engaged in DEAR time and BAN (Book A Night) Use of technology in literacy and numeracy programs Student participation in stage appropriate literacy lessons Teacher’s Day books note weekly focus. % parent involvement & learning outcomes Talking and listening timetabled and effectively implemented 1 term of Aboriginal Studies for all classes Assistants in 100% classes Attendance at Prof Dev Homework returned completed Student outcomes discussed at AEC meetings Community members discussing school and education issues and attending both meetings All staff aware of action plan Regular review of action plan Parents in joint projects with students using technology |           |             |           | All teaching staff Principal/teaching staff AERT All classroom teachers Teaching staff Principal/all staff “ AERT/AEO Principal Hwk centre staff Princ/AERT/AEO/AEA Principal Principal/AEO/AEA | 1000 2 000 5,400 62 000 6000 | Comp/coord/ Prof Dev(SiP) SiP SiP SiP/PSP | 50% students borrowing in 09. Tchrs to encourage BAN 2010 Effective technology use to be extended 2010 Learning focus to be more effectively relayed to students 92%= PLP attendance All classes Funding needed for hwk centre 2010 Re est local AECG 2010 First target not achieved in rdg or numeracy-all other targets achieved 2009 |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Schools In Partnership Outcomes 3 and 4. 100% of teaching programs demonstrate Quality Teaching Strategies in literacy and numeracy programs. % of students at stage appropriate level in literacy and numeracy to increase by 10% Increase Yr 3 students achieving bands 4,5&6 in literacy and numeracy by 10% Increase Yr 5 students achieving bands 6,7&8 by 10% Literacy and numeracy growth to equal state average. NP TARGETS Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 55% in 2010 to 66% in 2011 in NAPLAN Writing. Increase the number of students (in year 5) achieving in bands 6, 7 and 8 from 33% in 2010 to 55% in 2011 in NAPLAN Writing. Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 22% in 2010 to 33% in 2011 in NAPLAN Spelling. Increase the number of students (in year 5) achieving in bands 5, 6, 7 and 8 from 55% in 2010 to 66% in 2011 in NAPLAN Spelling. Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 33% in 2010 to 44% in 2011 in NAPLAN Grammar and Punctuation Increase the number of students (in year 5) achieving in bands 6, 7 and 8 from 11% in 2010 to 44% in 2011 in NAPLAN Grammar and Punctuation. | R3 R5 R1 R4 R4 R3 R4 R2 R1 R2,R5 R2,R5 | Regular Staff Development in QT framework and QT matrix. Staff involvement in coding lessons in literacy and numeracy. (video) Supervision of teaching programs monitoring QT strategies. Observation of ‘best practise’ in QT. Implementation of Accelerated Literacy program Staff Professional Development in modelled and guided reading and writing Integrated learning with writing focus. Intensive, supported small literacy and numeracy groups Implement whole school CMIT maths program Staff development in CMIT with Sue O’Reagan area consultant | Staff member as QT contact to monitor program 100% teachers engaged in QT coding Regular review of QT matrix 100% of programs have QT embedded with corresponding classroom practice. Accelerated Literacy units developed and shared. Explicit teaching focus evident in modelled and guided reading and writing Text type focus –evidence of literacy dev in Science, HSIE,CAPA , PDHPE Engaged small group learning Staff member as CMIT contact to monitor program |         |           |           | Marnie-QT contact/principal Supervisors/principal Classroom teachers Classroom teachers Principal CMIT contact/principal | 3000 2000 3000 1000 25000 1000 | SiP TPL funds SiP TPL funds SiP SiP | All tchrs engaged  Teachers released to dev lesson coding All targets achieved 2009; plan to improve by same % 2010 Literacy and numeracy growth greater than state 2009 |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Schools In Partnership Outcome No: 2 Improve student attendance Attendance to be 90% or greater School to match the Region’s attendance by 2012 Consistent improvement each year Improved parent/community involvement in attendance program |  | Early contact with parents/carers when attendance concerns arise. Student self monitoring of attendance Provision of absence notes in newsletter for families to return to school Attendance reward excursions for 90%+ every term. Attendance medallion awards at Annual Presentation for 95%+ attendance. Weekly visits to homes for positive feedback and attendance follow up Attendance data collected and collated week 4 and 8 every term. | Notes explaining absence returned to school Student charts in classroom Notes in newsletter returned Increase in no. of students on rewards excursion Increased no. of attendance medallions at Presentation Parents/carers engaging in visits to community Comprehensive term data reports to school community and regional office |        |        |        | Classroom Teachers/ AERT/AEO/AESS Classroom Teachers Principal /SAM Emily Maslen / Marnie Bailey Principal AERT/AEO/AESS Principal/ Classroom teachers | $3000 $200 | Grant-Syd Myer/Student welfare Global | Attendance 2009 greater than region and 1% less than state.(92%) |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Schools In Partnership Outcome Nos: 2 and 5 Aboriginal culture reflected in 100% teaching programs. 100% teaching programs have Aboriginal perspectives evident across KLAs Bundjalung language evident in all classrooms 100% teaching staff implementing Aboriginal studies program Local Cultural Resource Library established Establishment of Outdoor Education Area with family totems and local bush tucker. |  | Aboriginal perspectives included on teacher programming sheets Aboriginal Assistants in classrooms Local cultural resources made for all classrooms. Regular AEC meeting to monitor Aboriginal programs. Development of language DVD by Poppy Harry and AEO Development of literacy based Aboriginal Studies units Interest Enrichment Program to include Cultural units. Collation of local resources and history by staff and community. Partnership with community groups to develop Outdoor Education Area Resource Development days in Resource room | Evidence of Aboriginal perspectives in all classrooms Assistants in attendance Students involved in production and use of local resources Meeting minutes Bundjalung language evident in all classrooms Aboriginal studies in all classes Weekly interest groups with cultural perspective Local resource area developed. CDEP/Balunda assistance with project Attendance at resource days |       |         |       | All teaching staff Principal AERT/AEA/AEO Principal/AERT/AEA/AEO AEO AERT Marnie Bailey Aboriginal Education Committee Principal/AEO/SiP advisory committee AERT/AEO/AEA | 25,000 5 000 1500 2500 30 000 1 000 | SiP/Integration/Nortec Aboriginal Languages PSP/CAPA Aboriginal programs SiP AELDP | Started 2010 Almost complete(2010) |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Schools In Partnership Outcome No:5 Implementation of weekly pre-school to school transition program 100% students attend Prior to school transition program 100% students assessed on foundation outcomes Increased student readiness for Kindergarten Transition students on PLP program |  | Prior to School Transition Program to operate on school grounds every Monday for full school year. Trained teacher to facilitate Transition Program with assistant Starting School Packs provided to Transition students School shirts provided to Transition students Transition teacher to liaise with local Pre-school. Transition Program opened to all surrounding schools Parent meetings re PLP term 2 and term 4 | Transition days on Mondays with trained teacher. Programmed transition lessons Transition students utilising school packs Transition students wearing school shirts Regular meetings with local pre-school staff Attendance of students attending other schools in Kindergarten Parent attendance at meetings |        |        |  | Leanne Hore Leanne Hore Marnie Bailey/ Leanne Hore Leanne Hore Leanne Hore Leanne Hore | $25,000 $300 | SiP PSP | Progress to 1 full day per week has been extremely successful. 90% student attendance 100% students assessed on foundation outcomes Students settle into school very well and community very pleased with the program Best start data used at beg of Kinder to create PLP |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NP TARGETS Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 55% in 2010 to 66% in 2011 in NAPLAN Writing. Increase the number of students (in year 5) achieving in bands 6, 7 and 8 from 33% in 2010 to 55% in 2011 in NAPLAN Writing. Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 22% in 2010 to 33% in 2011 in NAPLAN Spelling. Increase the number of students (in year 5) achieving in bands 5, 6, 7 and 8 from 55% in 2010 to 66% in 2011 in NAPLAN Spelling. Increase the number of students (in year 3) achieving in bands 4, 5 and 6 from 33% in 2010 to 44% in 2011 in NAPLAN Grammar and Punctuation Increase the number of students (in year 5) achieving in bands 6, 7 and 8 from 11% in 2010 to 44% in 2011 in NAPLAN Grammar and Punctuation. | R3 R5 R1 R4 R4 R3 R4 R2 R1 R2,R5 R2,R5 | 1.Implementation of whole school approach to writing and Accelerated Literacy.(Format a weekly structure around a text type for the whole school to follow) 2.Whole school analysis of NAPLAN using SMART to identify strengths and weaknesses with alignment to syllabus outcomes 3.Teacher to lead the incorporation of teaching strategies from SMART data for identified outcomes into teaching and learning programs 4. Implementation of North Coast Spelling Strategy. 5. Professional development for Grammar and punctuation 6. Professional Development (Quality Teaching Conference) 2011 7. Use interactive Technology more effectively 8. Teacher to Review Accelerated Literacy and build teacher capacity 9. SDD Writing (open to cluster) 10.Exposure of students to a variety of assessment formats 11. Teacher professional learning plans- addressing outcomes for Aboriginal & non Aboriginal students. 12. Team Leadership for School Improvement | Explicit learning to and learning about focus for literacy in teaching programs. Teacher knowledgeable about and confident in addressing needs of students Staff meetings sharing successful strategies and team teaching Strategies evident in classrooms Completion of course Attendance at conference QT strategies evident in classrooms Lesson model and peer observation employed Course completed Development of resource Discussion of plans at TARS/program meetings Course Completed by Principal and NP Coordinator. Staff to complete course. |    |            |  | Principal and National Partnership Coordinator “ NP teacher Classroom teachers Principal Principal Classroom teachers NP teacher Principal Classroom teachers Supervisors/Classroom teachers | $5000 $25900 $5654 $32376 $2040 | NP NP NP NP NP |  |

| Expected Outcomes and Targets | Reform | Strategies | Indicators | 10 | 11 | 12 | Responsibility | Allocation | Funding Source | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Further development of teacher/community relationships to support student learning. | R1 R6 R6 R4 R6 R6,R1 | 1. School on Land Council Meeting agenda and attending local AECG meetings. 2. One social afternoon per term; casual get- to –know you activities(Afternoon games, sports, working bee, have fun) 3. Teacher profiles (publish in newsletter, posters around the school, make a year book) 4.PLPs 5. Teacher visits to community with AESS 6. Community Liaison Officer | School personnel in attendance at Land council, P&C and local AECG meetings Attendance at social afternoons Resource distributed to families 100% students on PLP Teacher visits to community once per term Employment of CLO one day per week |    |       |  | Principal & AEC members All staff Principal/SAM Classroom teachers AESS/teachers Principal | $14062 | SIP SiP NP |  |